## Project schedule
[6 empty] | Project start: | [7 empty] | 2026-05-06
[6 empty] | Display week: | [7 empty] | 1
[6 empty] | May | [27 empty] | June | [29 empty] | July | [30 empty] | August | [30 empty] | September
| TASK | PROGRESS | START | END | time axis 2026-05-04 to 2026-09-13
 | time axis 2026-05-04 to 2026-09-13
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Data-Collection & Preprocessing
| Reach out to volunteers | 100% | 2026-05-06 | 2026-05-24 | 19 | 2026-08-10: HOLIDAY
| Setup Github repo | 100% | 2026-05-10 | 2026-05-11 | [134 empty] | 2026-06-01 | 2026-06-14
| Collect data from volunteers/collate consent forms | 100% | 2026-05-25 | 2026-06-07 | 14 | [133 empty] | 2026-05-21 | 2026-06-15
| Data Cleaning & Session Construction | 100% | 2026-05-14 | 2026-06-08 | 26 | [133 empty] | 2026-05-21 | 2026-06-15
| Development & implementation on filtering of the session datasets | 100% | 2026-05-14 | 2026-06-08 | [134 empty] | 2026-06-16 | 2026-06-17
| Merge datasets | 100% | 2026-06-09 | 2026-06-10 | 2 | [133 empty] | 2026-05-30 | 2026-05-31
| Normalisation of features | 100% | 2026-06-10 | 2026-06-10 | 1 | [133 empty] | 2026-05-31 | 2026-05-31
| Split dataset into training, validation & testing segments | 100% | 2026-06-10 | 2026-06-10 | 1 | [133 empty] | 2026-05-31 | 2026-05-31
| Logistic Regression | [137 empty] | -10 | -10
| Definition of feature vectors | 100% | 2026-06-11 | 2026-06-12 | 2 | [133 empty] | 2026-06-01 | 2026-06-02
| Training & Vaildation on their respective sets | 100% | 2026-06-13 | 2026-06-13 | 1 | [133 empty] | 2026-06-12 | 2026-06-12
| Extract and inspect feature coefficients | 100% | 2026-06-13 | 2026-06-13 | [134 empty] | 2026-06-12 | 2026-06-12
| Random Forest | [137 empty] | -1 | -1
| Training & Evaluation on their respective sets | 100% | 2026-06-14 | 2026-06-16 | 3 | [133 empty] | 2026-06-13 | 2026-06-15
| Extract feature importances and compare with feature coefficients from Logistic Regression | 100% | 2026-06-17 | 2026-06-17 | 1 | [133 empty] | 2026-06-16 | 2026-06-16
| Recurrent Neural Network | [137 empty] | -1 | -1
| Define inputs for both RNN AND SASRec | 100% | 2026-06-18 | 2026-06-19 | 2 | [133 empty] | 2026-06-17 | 2026-06-18
| Implement recurrent hidden state & training loop | 100% | 2026-06-19 | 2026-06-22 | 4 | [133 empty] | 2026-06-18 | 2026-06-21
| Training & Vaildation on their respective sets using standard loss function & tune hyperparameters | 0% | 2026-06-23 | 2026-06-26 | 4 | [133 empty] | 2026-06-22 | 2026-06-25
| Debug & sense-check outputs | 80% | 2026-06-26 | 2026-06-26 | 1 | [133 empty] | 2026-06-25 | 2026-06-25
| SASRec | [137 empty] | -1 | -1
| Implement causal self-attention mechanism | 100% | 2026-06-27 | 2026-07-01 | 5 | [133 empty] | 2026-06-26 | 2026-06-30
| Implement causal mask & positional encoding | 100% | 2026-07-02 | 2026-07-04 | 3 | [133 empty] | 2026-07-01 | 2026-07-03
| Training & Vaildation on their respective sets using standard loss function & tune hyperparameters | 80% | 2026-07-05 | 2026-07-08 | 4 | [133 empty] | 2026-07-04 | 2026-07-07
| Full-system functional verification | 90% | 2026-07-09 | 2026-07-09 | 1 | [133 empty] | 2026-07-08 | 2026-07-08
| Loss Function Investigation | [137 empty] | -1 | -1
| Indepth research of DRrL, identify areas that need to to be adapted | 100% | 2026-07-10 | 2026-07-14 | 5 | [133 empty] | 2026-07-09 | 2026-07-13
| Implementation of adapted DRrL | 100% | 2026-07-15 | 2026-07-16 | 2 | [133 empty] | 2026-07-14 | 2026-07-15
| Training and validation of RNN & SASRec with adapted DRrL on respective sets | 0% | 2026-07-17 | 2026-07-19 | 3 | [133 empty] | 2026-07-16 | 2026-07-18
| Development & implementation of the combined custom loss function, PWTS | 60% | 2026-07-18 | 2026-07-20 | 3 | [133 empty] | 2026-07-17 | 2026-07-19
| Training and validation of RNN & SASRec with adapted PWTS on respective sets | 0% | 2026-07-21 | 2026-07-23 | 3 | [133 empty] | 2026-07-20 | 2026-07-22
| Evaluation | [137 empty] | -1 | -1
| Run all 4 models with standard BCE loss function on held-out test set and evaluate with AUC-ROC, MRR & NDCG | 0% | 2026-07-23 | 2026-07-24 | 2 | [133 empty] | 2026-07-25 | 2026-07-26
| Run RNN & SASRec with DRrL and PWTS loss functions on held-out test set and evaluate with the above metrics | 0% | 2026-07-24 | 2026-07-26 | 3 | [133 empty] | 2026-07-26 | 2026-07-28
| Produce comparison table for each of these comparisons | 0% | 2026-07-27 | 2026-07-27 | 1 | [133 empty] | 2026-07-29 | 2026-07-29
| Indentify best performing combinations | 0% | 2026-07-27 | 2026-07-27 | [134 empty] | 2026-07-29 | 2026-07-29
| Report Writing | [137 empty] | 1900-01-01 | 1900-01-01
| Write Methodology chapter | 0% | 2026-05-27 | 2026-07-31 | 66 | [133 empty] | 2026-05-29 | 2026-08-02
| Write Inttroduction & Literature Review chapters | 0% | 2026-06-15 | 2026-07-31 | 47 | [133 empty] | 2026-06-17 | 2026-08-02
| Interpret Skip-probability and Queue-Reordering results |  | 2026-07-28 | 2026-07-30 | [134 empty] | 2026-07-30 | 2026-08-01
| Write Evaluation & Results chapters |  | 2026-07-31 | 2026-08-02 | [134 empty] | 2026-08-02 | 2026-08-04
| Write up any limitations/unexpected findings |  | 2026-08-03 | 2026-08-04 | [134 empty] | 2026-08-05 | 2026-08-06
| Write conlusion, absract chapters |  | 2026-08-05 | 2026-08-06 | [134 empty] | 2026-08-07 | 2026-08-08
| Proof-read, format & bibliography |  | 2026-08-07 | 2026-08-09 | [134 empty] | 2026-08-09 | 2026-08-11
| Buffer |  | 2026-08-24 | 2026-09-10
| Deadline |  | 2026-09-11 | 2026-09-11